## Slide 1: Seattle Channel Committee
Beryl Fernandes, Chair
CTTAB members: Nourisha Wells, Rob Dolin, Ivan Orbegozo, Stacey Wedlake, Eric Nelson, Justin Almeida, Gabriel Schubiner
Staff: John Giamberso, Lori Patrick, Curt Weiss
SEATTLE CHANNEL
COMMITTEE WORKPLAN
2013

## Slide 2: Seattle Channel Committee
MISSION
Serve as a resource to the City of Seattle’s public TV station in implementing its mandate to help foster an informed and actively engaged citizenry.
Committee members will provide advice, review and comment on staff and consultant recommendations.

## Slide 3: Seattle Channel Meetings
2nd Tuesday of each month
4.45pm to 5.45pm
Seattle Channel Office, City Hall

## Slide 4: COMMITTEE MEMBERS
Chair: Beryl Fernandes
Vice-Chair: Rob Dolin (interim-anyone else interested?)
Recorder: ? (any takers?)
Members: Stacey Wedlake, Nourisha Wells, Eric Nelson, Justin Almeida, Ivan Orbego, Gabriel Schubiner
Staff: John Giamberso, General Manager, Seattle Channel; Lori Patrick, Communications Manager; Curt Weiss, Operations Manager

## Slide 5: Work Plan Priorities
  1) Revised Seattle Channel Mandate
  - Recommend revisions
    - Conduct monthly reviews and updates of drafts
    - Present final draft to CTTAB
  2) Marketing Strategy
  - Review and comment on SC’s new Marketing Strategy
    Participate as appropriate in focus groups, among other mechanisms for comment
  3) Government Channel Survey
  - Recommendations on SC staff’s survey

## Slide 6: Revised SC Mandate
Goals / Description: Review previous mandate and recommend changes
Deliverable: Recommendations on Revised SC Mandate
Timeline:
  June 11, Review draft outline
  July 9 submit recommendations
  August 13 review revised draft
  September 10, finalize document
  October 8, present to CTTAB for review
  November 12, sign completed document
Project leads: Lori Patrick, Curt Weiss, others?

## Slide 7: Revised Mandate starting w Executive Summary (cont’d)
Content and Production
    Types of multi-media resources to provide information and interactivity
    Making programming (production and scheduling) engaging, compelling and informative
    New content ideas, new scheduling ideas
Technology
    Use of new technology to increase interactivity, Provide information to residents
    Abandon old technologies, i.e. television channels or Retain them in current state or adopt some mix of the two?
Partnerships
    Identify institutions with similar goals
    What might these partnerships look like?
Finance
    Identify sources of revenue in addition to the Cable fund
    Justifications to increase cable franchise fees
    What level and kinds of support to request-new 2016 Comcast franchise
Branding and Marketing
    Changes and improvements to current Seattle Channel brand – name, logo, website
    Recommendations to current development of marketing plan
Governance and Evaluation
    Review reports on new programs developed, number and kind of programs produced, website statistics, audience surveys

## Slide 8: Revised Marketing Strategy
Goals / Description: Review and Comment on Staff and Consultant’s revised marketing strategy
Deliverable: Recommendations on Revised Brand Statement
Timeline: July 2013
Project lead(s): Beryl, Others (please add names)

## Slide 9: Government Channel Survey
Review and make recommendations to SC staff on the survey of government channels
Explore implications for SC on how they approach changing technology, changing audience demographics, financial models

## Slide 10: General Questions
Accessibility
Inclusivity and Diversity
Openness
Privacy
Security
Notes: Let’s hold on this until I get some clarification from Rob

## Slide 11: Accessibility
How are you considering accessibility?

## Slide 12: Inclusivity and Diversity
How are you considering inclusivity and diversity?

## Slide 13: Transparency
How are you considering transparency?

## Slide 14: Privacy
How are you considering privacy?